## Web Features
Sl no. | TestCase ID | Feature name | Actions | WBS Hours | Resource Name | Exp. Completion Date (Development) | Exp. Test Server Release Date | Actual Test Server Release Date | QA Start Date | QA End Date | Testing Time (hrs) | Bug Number | Solved Bug | Release Date(Bug /Feedback fixing) | Regression/Retesting Start Date | Regression/Retesting End Date | Regression/Retesting Hour | Total Hour | Comments
1 | TS_COM_001-2 | Company | Create | 2 | Saifur | 2022-09-04 | 2022-09-05 |  |  |  |  | NGLSC-1255, NGLSC-1135 Rakib:1948, 1475
Update
List
Product - View
2 | TS_LOC_001-2 | Location | Create | 2 | Saifur | 2022-09-05 | 2022-09-06
Update
List
Search
Product - View
3 | TS_DEP_001-2 | Depot Configure | Create | 2 | Saifur | 2022-09-06 | 2022-09-07 |  |  |  |  | NGLSC-527, NGLSC-528 Rakib:1477,
Update
List
Search
Product - View
Depot Company Mapping
4 |  | Product Configure | Category Level - Create | 10 | Tamanna | Done | 2022-07-27 | 2022-07-27 | 2022-08-02 | 2022-08-02 | 8 | NGLSC-641, NGLSC-642, NGLSC-787, NGLSC-788,NGLSC-789, NGLSC-790, NGLSC-791, NGLSC-792, NGLSC-793, NGLSC-794, NGLSC-1088, NGLSC-1087, NGLSC-796, NGLSC-795,
Category Level - View
Category Level - Update
Category Level - Delete
5 |  |  | Category Tree - Create |  | Tamanna | Done | 2022-07-27 | 2022-07-27
Category Tree - View
Category Tree - Update
Category Tree - Delete
6 |  |  | Product - Create |  | Tamanna | 2022-09-06 | 2022-09-07 | 2022-07-27
Product - View
Product - Update
Product - Delete
Product - List
Product - Search
7 |  | Sales Data | List View | 0.5 | Tamanna | 2022-09-08 | 2022-09-11 | 2022-09-12 | 2022-10-26 | 2022-10-26 |  | NGLSC-1427,NGLSC-1428,NGLSC-1429,NGLSC-1430,NGLSC-1431
Search
Excel Export
8 | TC_SB_001-TC_SB_007 | Sales Booking | List View | 1 | Tamanna | 2022-09-08 | 2022-09-11 | 2022-09-12 | 2022-09-13 | 2022-09-13 |  | NGLSC-1019, NGLSC-1020, NGLSC-1021, NGLSC-1023, NGLSC-1024, | NGLSC-1026, NGLSC-1025, NGLSC-1022,
Search
Detail View
Excel Export
9 |  | Sales Order | List View | 1 | Saifur | 2022-09-08 | 2022-09-11 | 2022-09-12
Search
Detail View
Excel Export
10 | TC_SR_001-TC_SR_010 | Sales Return | List View | 1 | RAKIB | 2022-09-08 | 2022-09-11 | 2022-09-12 | 2022-10-23 | 2022-10-23
Search
Detail View
Excel Export
11 |  | Trade Price | List View | 1.5 | Tamanna | 2022-09-08 | 2022-09-11 | 2022-09-12
Search
Action(View, Edit, Delete)
Excel Export
12 |  | Trade Discount | List View | 1.5 | Tamanna | 2022-09-11 | 2022-09-12 | 2022-09-12 |  |  | 2 hr
Search
Action(View, Edit, Delete)
Excel Export
13 |  | Sales Budget | List View | 0.5 | Saifur | 2022-09-11 | 2022-09-12 | 2022-09-12
Search
Excel Export
14 | TC_P-C_001 | Collection Data | List View | 2 | Rakib | 2022-09-11 | 2022-09-12 | 2022-09-12
Search
Detail View
Excel Export
15 | TC_ORD_001 | ORD | List View | 0.5 | Tamanna | 2022-09-11 | 2022-09-12 | 2022-09-12
Search
Detail View
Excel Export
16 | TC_OC_001-TC_OC_003 | ORD Calculator | List View | 0.5 | Tamanna | 2022-09-11 | 2022-09-12 | 2022-09-12
Search
Detail View
Excel Export
17 |  | Collection Budget | List View | 0.5 | Saifur | 2022-09-11 | 2022-09-12 | 2022-09-12
Search
Excel Export
18 |  | Distributor/Distributor List | List View | 1 | Tamanna | 2022-08-14 | 2022-08-16 | 2022-08-20 | 22/08/2022 | 25/08/2022 | 1h | NGLSC-751, NGLSC-759, NGLSC-760, NGLSC-761, NGLSC-762, NGLSC-783, NGLSC-785
Search
Detail View
Excel Export
19 | TC_C-L_001 | Distributor/Credit Limit Proposal | List View | 1 | Tamanna | 2022-08-16 | 2022-08-17 | 20-Aug-2022 Testing cannot start due to depends on Mobile Application
Search
Detail View
Excel Export
20 |  | Distributor/CRUD | Create | 3 | Tamanna | 2022-08-11 | 2022-08-14 | 2022-08-20 | 22/08/2022 | 25/08/2022 | 3h | NGLSC-752, NGLSC-753, NGLSC-755, NGLSC-756, NGLSC-757, NGLSC-763, NGLSC-778, NGLSC-784, NGLSC-786, NGLSC-1092
Update
File Upload
21 |  | Invoice | List View Distributor Wise | 5 | Tamanna | 2022-08-11 | 2022-08-14 | 20-Aug-2022 Testing cannot start due to invoice entry screen is not available | 27/10/2022 |  |  | Rakib: BUG: NGLSC-1269
List View Sales Officer Wise
Search
Distributor Wise Detail View
Sales Officer Wise Detail View
Invoice Details
Excel Export
22 | TC_FY_001-TC_FY_002 | Timeline Setup | Create | 1 | Rakibul | 2022-08-09 | 2022-08-10 | 2022-08-20 | 2022-08-21 | 2022-08-21 |  | Main Task: NGLSC-415 Bug: (6) NGLSC-722, NGLSC-727, NGLSC-730, NGLSC-731, 1271,1272 Improvement: (3) NGLSC-729, NGLSC-936, 1273 | NGLSC-723, NGLSC-724, NGLSC-725, NGLSC-726, NGLSC-728, NGLSC-718, NGLSC-721, NGLSC-720, NGLSC-732,
Update
List View
Search
Detail View
23 | TC_TP_001-4 | Trade price setup | Create(price,vat) | 2 | Tamanna | 2022-08-14 | 2022-08-16 | 2022-08-20 | 2022-08-23 | 2022-08-23 | 2 hr | NGLSC-736, NGLSC-737, NGLSC-738, NGLSC-739, NGLSC-740, NGLSC-743, NGLSC-744, NGLSC-745, NGLSC-746, NGLSC-990, NGLSC-991, NGLSC-993, NGLSC-994, NGLSC-996, NGLSC-997, NGLSC-998, NGLSC-999, NGLSC-1030
Update(price,vat)
List View(price,vat)
Search(price,vat)
Detail View(price,vat)
24 | TC_TD_001-2 | Trade Discount setup | Create | 2 | Tamanna | 2022-08-17 | 2022-08-18 | 2022-08-20 | 2022-08-24 | 2022-08-24 | 2 hr | NGLSC-764, NGLSC-765, NGLSC-766, NGLSC-769, NGLSC-770, NGLSC-1003, NGLSC-1004, NGLSC-1005
Update
List View
Search
Detail View
25 |  | Budget setup/Distributor Wise | Sale Budget/Upload & Create | 1 | Saifur | 2022-08-18 | 2022-08-21 | 2022-08-27
Sale Budget/List View
Sale Budget/Download Format
Collection Budget/Upload & Create
Collection Budget/List View
Collection BudgetDownload Format
26 | TC_ORD_001 TC_ODS_001 | ORD & Overdue Setup | ORD/Create | 3 | Tamanna | 2022-08-23 | 2022-08-24 | 2022-08-27 | 2022-08-29 | 2022-08-29 |  | NGLSC-808, NGLSC-809, NGLSC-826, NGLSC-827, NGLSC-820, NGLSC-821, NGLSC-822
ORD/Update
ORD/List
ORD/Approval
Overdue/Create
Overdue/Update
Overdue/List
27 | TC_PBS_001-TC_PBS_005 | Payment Book Setup | Create | 3 | Tamanna | 2022-08-22 | 2022-08-23 | 2022-09-03 | 2022-09-04 | 2022-09-04 |  | NGLSC-869, NGLSC-870, NGLSC-871, NGLSC-872, NGLSC-873, NGLSC-874, NGLSC-875, NGLSC-877, NGLSC-878, NGLSC-879, NGLSC-880, NGLSC-881, NGLSC-882, NGLSC-883, NGLSC-884, NGLSC-885, NGLSC-890 Rakib:(New BUG) NGLSC-1032, NGLSC-1033, NGLSC-1035, NGLSC-1036, NGLSC-1037, NGLSC-1039, NGLSC-1040, NGLSC-1041, NGLSC-1072, NGLSC-1074
Update
List
Search
28 | TC_Pvr_001 -5 TC_PAD_001 TC_CN_001-TC_CN_008 TC_DN_001-TC_DN_007 | Payment Adjustment | Adjustment Todays Summery | 20 | Tamanna | 2022-08-18 | 2022-08-21 | 20-Aug-2022 Testing cannot start due to depends on other feature(Sales Booking, Sales Order etc.) | 13/10/2022 | 13/10/2022 |  | Rakib: BUG: 1312
Payment Verify -> Payment List
Payment Verify -> Filter/Search
Payment Verify -> Excel Export
Payment Verify -> Verify Action Detail
Payment Verify -> Verify Action Approval
Payment Verify -> Verify Action Download
Payment Verify -> Confirm & Show Details
29 |  |  | Payment Adjustment -> Adjustment List |  |  | 2022-08-25 | 2022-08-28 | 2022-09-14 | 16/10/2022 | 16/10/2022 |  | NGLSC-1371,NGLSC-1376,NGLSC-1377,NGLSC-1378,NGLSC-1382,NGLSC-1383,NGLSC-1279,NGLSC-1384,NGLSC-1385,NGLSC-1386,NGLSC-1397
Payment Adjustment -> Filter/Search
Payment Adjustment -> Excel Export
Payment Adjustment -> Adjustment Detali
Payment Adjustment -> Adjustment Submit
Payment Adjustment -> Adjustment History
Payment Adjustment -> History Excel Export
30 |  |  | ORD Settlement -> Payment List |  |  | 2022-08-30 | 2022-08-31 | 2022-09-17
ORD Settlement -> Filter/Search
ORD Settlement -> Excel Export
ORD Settlement -> Action Submit
31 |  |  | Credit/Debit Note -> List View |  | Rakib | 2022-08-30 | 2022-08-31 | 5-Sep-2022 Testing cannot start due to depends on other feature(Sales Booking, Sales Order Invoice etc.)
Credit/Debit Note -> Filter/Search
Credit/Debit Note -> View Details(Ledger)
Credit/Debit Note -> Credit Note Create
Credit/Debit Note -> Debit Note Create
Credit/Debit Note -> Approvals List
Credit/Debit Note -> Approvals Summery
Credit/Debit Note -> Approvals Activity
32 |  | Production -> Batch Preparation | List | 5 | Tamanna |  |  | 3-Sep-2022 Hold for design issue 14-Sep-2022 Again release with enhancement | 2022-09-15 | 2022-09-15 |  | NGLSC-1094, NGLSC-1095, NGLSC-1096, NGLSC-1097, NGLSC-1237, NGLSC-1098, NGLSC-1099, NGLSC-1100, NGLSC-1101, NGLSC-1102, NGLSC-1105,
Create
View (Stock Data)
View (Batches & QR Code)
View (QR)
33 |  |  | Stock Data -> List
Stock Data -> View
34 |  |  | Sales Order -> Sales Booking -> List | 4.5 | Tamanna |  |  | 2022-09-12 | 2022-09-14 | 2022-09-14 |  | NGLSC-1046, NGLSC-1047, NGLSC-1049, NGLSC-1050, NGLSC-1051, NGLSC-1054, NGLSC-1060, NGLSC-1061, NGLSC-1060, NGLSC-1073, NGLSC-1075, NGLSC-1076, NGLSC-1077, Rakib: BUG:02 NGLSC-1309, NGLSC-1310
Sales Order -> Sales Booking -> Approval
Sales Order -> Sales Booking -> Tickets
35 |  |  | Sales Order -> Sales Order -> List | 5 | Saifur |  |  | 2022-09-14 |  |  |  | NGLSC-1270, NGLSC-1284, NGLSC-1285, NGLSC-1286, NGLSC-1287
Sales Order -> Sales Order -> Add Order
Sales Order -> Sales Order -> View
36 |  |  | Sales Order -> Picking -> List |  | Tamanna |  | 2022-10-03 |  |  |  |  | NGLSC-1415,NGLSC-1416,NGLSC-1417,NGLSC-1418,NGLSC-1419,NGLSC-1420,NGLSC-1421,NGLSC-1422,NGLSC-1423,NGLSC-1424
Sales Order -> Picking -> Create
Sales Order -> Picking -> View
37 |  |  | Sales Order -> Delivery Challan -> List | 5 | Tamanna |  | 2022-09-14 | 2022-09-14 |  |  |  | NGLSC-1328,NGLSC-1329,NGLSC-1331,NGLSC-1332,NGLSC-1333,NGLSC-1334,NGLSC-1336,NGLSC-1338,NGLSC-1342,NGLSC-1343,NGLSC-1344,NGLSC-1345,NGLSC-1347,NGLSC-1348,NGLSC-1406,NGLSC-1407,NGLSC-1408
|  |  | Sales Order -> Delivery Challan -> Create | [8 empty] | Rakib: NGLSC-1354, NGLSC-1355, NGLSC-1356
Sales Order -> Delivery Challan -> View
38 |  |  | Sales Order -> Invoices -> List | 5 | Tamanna |  | 2022-09-13 | 2022-09-14 |  |  |  | NGLSC-1439,NGLSC-1441,NGLSC-1442,NGLSC-1443,NGLSC-1444,NGLSC-1445
Sales Order -> Invoices -> Create
Sales Order -> Invoices -> View
39 |  | Stock -> Transfer | Production Receive -> List | 5 | Tamanna | Development Inprogress |  | 2022-09-15 |  |  |  | NGLSC-1212, NGLSC-1213, NGLSC-1216, NGLSC-1217, NGLSC-1228, NGLSC-1230, NGLSC-1231, NGLSC-1232, NGLSC-1233, NGLSC-1236, NGLSC-1262
Production Receive -> Create
Production Receive -> View
40 |  |  | Inventory Transfer -> List |  | Tamanna | Development Inprogress |  | 2022-09-17 |  |  |  | NGLSC-1241, NGLSC-1243, NGLSC-1244, NGLSC-1246, NGLSC-1263
Inventory Transfer -> Create
|  |  | Inventory Transfer -> View | [8 empty] | NGLSC-1247, NGLSC-1249, NGLSC-1250, NGLSC-1251, NGLSC-1252, NGLSC-1253, NGLSC-1254, NGLSC-1256, NGLSC-1257, NGLSC-1264
41 |  |  | Store Transfer -> List |  | Saifur |  | 2022-10-03 |  |  |  |  | Rakib: NGLSC-1313, NGLSC-1335, NGLSC-1337, NGLSC-1339, NGLSC-1340, NGLSC-1341
Store Transfer -> Create
Store Transfer -> View
42 |  |  | Damage Declaration -> List |  | Rakib |  | 2022-10-06 |  |  |  |  | NGLSC-1372, NGLSC-1373,
Damage Declaration-> Create
Damage Declaration -> View
43 |  |  | Sales Return -> List |  | Rakib |  | 2022-10-02 |  |  |  |  | NGLSC-1435, NGLSC-1436,NGLSC-1434,
|  |  | Sales Return-> Receive | [8 empty] | NGLSC-1412,NGLSC-1349, NGLSC-1350, NGLSC-1351, NGLSC-1352, NGLSC-1353
Sales Return -> View
44 |  | Multi Layer Approval | Domain Design | 5 | Saifur |  |  | 2022-09-14
Create
Update
List
Deatils View
45 |  | Configure | Bank -> Create | 3.75 | Tamanna | 2022-08-31 | 2022-09-01 | 2022-09-03 | 2022-09-05 | 2022-09-05 | 2 | NGLSC-894, NGLSC-895, NGLSC-896, NGLSC-897
Bank -> Update
Bank -> List
Bank -> Deatils View
46 |  |  | Branch -> Create | 3.75 | Tamanna |  |  | 2022-09-07 | 2022-09-08 | 2022-09-08 | 3.5 | NGLSC-924, NGLSC-925, NGLSC-926, NGLSC-927, NGLSC-928, NGLSC-929, NGLSC-930, NGLSC-931, NGLSC-934, NGLSC-935 Rakib: BUG: 02 NGLSC-1200, NGLSC-1199
Branch -> Update
Branch -> List
Branch -> Deatils View
47 |  |  | Bank Account -> Create | 3.75 | Tamanna |  |  | 7-Sep-2022 Back to Development 14-Sep-2022 Again Release |  |  |  | NGLSC-1156, NGLSC-1113
Bank Account -> Update
Bank Account -> List
Bank Account -> Deatils View
48 |  |  | Currency-> Create | 3.75 | Tamanna |  |  | 2022-09-07 | 2022-09-08 | 2022-09-08 |  | NGLSC-937, NGLSC-939, NGLSC-940
Currency -> Update
Currency -> List
Currency -> Deatils View
49 |  |  | Designation -> Create | 3.75 | Tamanna |  |  | 2022-09-07 | 2022-09-10 | 2022-09-10 | 3.5 | NGLSC-944, NGLSC-945, NGLSC-946 Rakib: BUG:02 NGLSC-1214, NGLSC-1215
Designation -> Update
Designation -> List
Designation -> Deatils View
50 |  |  | Department -> Create | 3.25 | Tamanna |  |  | 2022-09-03 | 2022-09-05 | 2022-09-05 | 2 | NGLSC-891, NGLSC-892, NGLSC-893 Rakib: Bug: NGLSC-1223
Department -> Update
Department -> List
Department -> Deatils View
51 |  |  | Store -> Create | 4 | Tamanna |  |  | 2022-09-05 | 2022-09-05 | 2022-09-05 | 2 | NGLSC-901, NGLSC-902, NGLSC-903, NGLSC-904 Rakib: Bug:01 NGLSC-1201, NGLSC-1202 Improvement: NGLSC-1203
Store -> Update
Store -> List
Store -> Deatils View
52 |  |  | Unit of Measurement -> Create | 4 | Tamanna |  |  | 2022-09-05 | 2022-09-06 | 2022-09-06 | 2 | NGLSC-908, NGLSC-909, NGLSC-910, NGLSC-911 Rakib BUG:01 NGLSC-1204
Unit of Measurement -> Update
Unit of Measurement -> List
Unit of Measurement -> Deatils View
53 |  |  | Pack Size -> Create | 4 | Saifur |  |  | 2022-09-05 | 2022-09-05 | 2022-09-05 |  | NGLSC-966, NGLSC-989, NGLSC-992 Rakib BUG: NGLSC-1207, NGLSC-1208, NGLSC-1209, NGLSC-1210 IMP: NGLSC-1206
Pack Size -> Update
Pack Size -> List
Pack Size -> Deatils View
54 |  | User Management | User -> Create | 5 | Saifur |  |  | 2022-09-07 | 2022-09-08 | 2022-09-11 |  | NGLSC-973, NGLSC-983, NGLSC-987, NGLSC-984, NGLSC-974 Rakib: Main Task: NGLSC-468 BUG (4) : NGLSC-1167, NGLSC-1170, NGLSC-1171 , NGLSC-1172, IMP (3) : NGLSC-1168, NGLSC-1169, NGLSC-1173, NGLSC-1198
User -> Update
User -> List
User -> Deatils View
55 |  |  | Role -> Create | 5 | Saifur |  |  | 2022-09-12 | 2022-09-12 | 2022-09-13 |  | NGLSC-1011, NGLSC-1045 Rakib: Main Task: NGLSC-922 BUG (2) : NGLSC-1174, NGLSC-1175 IMP (1) : NGLSC-1176
Role -> Update
Role -> List
Role -> Deatils View
56 |  |  | User Role Mapping -> Create | 5 | Rakib |  | 2022-09-13 | 2022-09-14 | 2022-09-15 | 2022-09-15 |  | BUG: NGLSC-1082, NGLSC-1084, NGLSC- 1085 IMPROVEMENT: NGLSC-1078, NGLSC-1079, NGLSC-1080, NGLSC-1081, NGLSC-1083
User Role Mapping -> Update
User Role Mapping -> List
User Role Mapping -> Deatils View
57 |  |  | User Company Mapping -> Create | 5 | Saifur |  |  | 2022-09-12 | 2022-09-13 | 2022-09-13 |  | NGLSC-1028, NGLSC-1029, NGLSC-1031 Rakib: Main Task: NGLSC-919 BUG (1) : NGLSC-1177, NGLSC-1179 IMP (0) :
User Company Mapping -> Update
User Company Mapping -> List
User Company Mapping -> Deatils View
58 |  |  | Permission -> Create | 5 | Rakib
Permission -> Update
Permission -> List
Permission -> Deatils View
Permission Implementation
59 |  | Vehicle | Create | 2.5 | Tamanna |  |  | 2022-09-17 | 2022-09-19 | 2022-09-19 |  | NGLSC-1155, NGLSC-1211 | NGLSC-1150, NGLSC-1151, NGLSC-1152, NGLSC-1153, NGLSC-1154,
Update
List
Delete
60 |  | Credit Limit Setup | Create | 2.5 | Tamanna |  |  | 2022-09-17 | 2022-09-19 | 2022-09-19 |  | NGLSC-1163, NGLSC-1265, NGLSC-1266 | NGLSC-1159, NGLSC-1160, NGLSC-1161, NGLSC-1162,
Update
List
Delete
61 |  | Depot Location Level Setup | Create | 2.5 | Rakib |  |  | 2022-09-17 |  |  |  | Main Issue: NGLSC-1066 BUG: 02 NGLSC-1293, NGLSC-1294 IMP:1 NGLSC-1295
Update
List
Delete
62 |  | Reporting manager map | Create | 2.5 | Rakib |  |  | 2022-09-17 |  |  |  | Main Issue: NGLSC-1062 BUG: NGLSC-1134, NGLSC-1137, NGLSC-1234, NGLSC-1235, NGLSC-1308 IMP: NGLSC-1138, NGLSC-1139
Update
List
Delete
63 |  | Location manager map | Create | 2.5 | Rakib |  |  | 2022-09-17 |  |  |  | Main Task: NGLSC-1108 BUG: NGLSC-1131, NGLSC-1136, NGLSC-1307 IMP: NGLSC-1140
Update
List
Delete
64 |  | Stock -> Transfer | Inventory Transfer(Receive) -> List |  | Saifur |  |  | 2022-09-17 |  |  |  | Rakib: NGLSC-1367, NGLSC-1354, NGLSC-1368, NGLSC-1369, NGLSC-1370
Inventory Transfer(Receive) -> Create
Inventory Transfer(Receive) -> View
65 |  |  | Quality Assurance -> List |  |  |  | 2022-10-06
Quality Assurance -> Create
Quality Assurance -> View
66 |  | Distributor Credit Limit Setup | Create |  | Tamanna
Update
List
Delete
67 |  | Material Planner Confirmation | Create
Update
List
Delete
68 |  | Claim

## Web & Mobile Features Summary
Total feature | No. accepted feature for (15th September) | No. of Feature develop | Remaining Feature | Remaining feature after 15th September | No. of feature tested | No. of WIP feature for testing
76 | 59 | 73 | 2 | 2 | 68 | 5

## Remaining Task Web Feature
Index | Feature Name | Actions | Liton | Nisa | Amit | Mou | Sagor | Sony | Sunipa | Anika | Shohag(UX) | Leon | Saifur | Tamanna | Rakib(partial) | Total Hour | Exp. Dev. Completion Date | Exp. Test Completion Date
1 | Company | View |  |  |  | 2 | 4 |  |  | 0 | 0 | 0 | 1 | 0 | 0 | 7 | 2022-09-04 | 2022-09-05
2 | Location | View |  |  |  | 4 |  | 5 |  |  | 0 |  | 1 |  |  | 10 | 2022-09-05 | 2022-09-06
3 | Depot Configure | View |  |  |  | 2 |  | 4 |  |  | 0 |  | 1 |  |  | 7 | 2022-09-06 | 2022-09-07
|  | Depot Company Mapping |  |  |  | 4 |  | 10 |  |  | 0 |  | 1 |  |  | 15
4 | Product Configure | Product - View | 6 |  |  | 4 |  |  |  |  | 0 |  |  | 1 |  | 11 | 2022-09-06 | 2022-09-07
5 | Sales Data | Search |  |  | 6 | 8 | [7 empty] | 1 |  | 15 | 2022-09-08 | 2022-09-09
6 | Sales Booking | Search |  |  |  | 3 |  |  | 6 |  |  |  |  | 1 |  | 10 | 2022-09-08 | 2022-09-09
|  | Detail View |  |  |  | 5 |  |  | 8 |  |  |  |  | 1 |  | 14
7 | Sales Order | Search |  |  | 4 | 3 | [7 empty] | 1 |  | 8 | 2022-09-08 | 2022-09-09
|  | Detail View |  |  | 8 | 5 | [7 empty] | 1 |  | 14
8 | Sales Return | Search |  |  | 4 | 3 | [7 empty] | 1 |  | 8 | 2022-09-08 | 2022-09-09
|  | Detail View |  |  | 8 | 5 | [7 empty] | 1 |  | 14
9 | Trade Price | Search |  |  |  | 2 |  | 4 |  |  |  |  | 1 |  |  | 7 | 2022-09-08 | 2022-09-09
|  | Action(View, Edit, Delete) |  |  |  | 5 |  | 8 |  |  | 0 |  | 2 |  |  | 15
|  | Excel Export | [7 empty] | 2 |  |  | 0.5 |  |  | 2.5
10 | Trade Discount | Search |  |  |  | 2 | 4 | [5 empty] | 1 |  |  | 7 | 2022-09-11 | 2022-09-12
|  | Action(View, Edit, Delete) |  |  |  | 5 | 8 |  |  |  | 0 |  | 2 |  |  | 15
|  | Excel Export | [7 empty] | 2 |  |  | 0.5 |  |  | 2.5
11 | Sales Budget | Search |  |  | 4 | [9 empty] | 1 | 5 | 2022-09-11 | 2022-09-12
|  | Excel Export | [7 empty] | 2 |  |  |  |  | 0.5 | 2.5
12 | Collection Data | Search | [6 empty] | 4 |  |  |  |  | 1 |  | 5 | 2022-09-11 | 2022-09-12
|  | Detail View | [6 empty] | 8 |  |  |  |  | 1 |  | 9
|  | Excel Export | [7 empty] | 2 |  |  |  | 0.5 |  | 2.5
13 | ORD | Search | [6 empty] | 4 |  |  |  |  | 1 |  | 5 | 2022-09-11 | 2022-09-12
|  | Detail View | [6 empty] | 8 |  | 0 |  |  | 1 |  | 9
|  | Excel Export | [7 empty] | 2 |  |  |  | 0.5 |  | 2.5
14 | ORD Calculator | Search |  |  |  | 2 |  | 4 | [5 empty] | 1 |  | 7 | 2022-09-11 | 2022-09-12
15 | Collection Budget | Search |  |  | 4 | [8 empty] | 1 |  | 5 | 2022-09-11 | 2022-09-12
|  | Excel Export | [7 empty] | 2 |  |  |  | 0.5 |  | 2.5
16 | Distributor/Distributor List | Detail View |  |  |  | 4 | 8 |  |  |  | 8 |  |  | 1 |  | 21 | 2022-09-12 | 2022-09-13
0
17 | Distributor/Credit Limit Proposal | Detail View |  |  |  | 4 | 12 |  |  |  | 8 |  |  | 1 |  | 25 | 2022-09-12 | 2022-09-13
18 | Distributor/CRUD | Update |  |  |  |  | 8 | [6 empty] | 1 |  | 9 | 2022-08-23 | 2022-08-24
19 | Invoice | List View Sales Officer Wise |  |  | 4 | [8 empty] | 0.5 |  | 4.5 | 2022-09-12 | 2022-09-13
|  | Sales Officer Wise Detail View |  |  | 8 | [8 empty] | 0.5 |  | 8.5
|  | Invoice Details |  |  | 8 | [5 empty] | 8 |  |  | 1 |  | 17
20 | Budget setup/Distributor Wise | Sale Budget/Upload & Create |  |  | 8 | [9 empty] | 1 | 9 | 2022-08-25 | 2022-08-27
|  | Sale Budget/List View |  |  | 4 | [9 empty] | 0.5 | 4.5
|  | Sale Budget/Download Format |  |  | 4 | [9 empty] | 0.5 | 4.5
|  | Collection Budget/Upload & Create |  |  | 8 | [9 empty] | 1 | 9
|  | Collection Budget/List View |  |  | 4 | [9 empty] | 0.5 | 4.5
|  | Collection BudgetDownload Format |  |  | 4 | [9 empty] | 0.5 | 4.5
21 | ORD & Overdue Setup | ORD/Create | [5 empty] | 4 | [5 empty] | 2 |  | 6 | 2022-08-28 | 2022-08-29
|  | ORD/Update | [5 empty] | 4 | [5 empty] | 1 |  | 5
|  | ORD/List | [5 empty] | 2 | [5 empty] | 0.5 |  | 2.5
|  | ORD/Approval |  | 8 | [6 empty] | 0 |  |  | 0.5 |  | 8.5
|  | Overdue/Create | [5 empty] | 5 | [5 empty] | 2 |  | 7
|  | Overdue/Update | [5 empty] | 5 | [5 empty] | 1 |  | 6
|  | Overdue/List | [5 empty] | 6 | [5 empty] | 0.5 |  | 6.5
22 | Payment Book Setup | Create | [7 empty] | 4 |  |  |  |  | 1 | 5 | 2022-08-28 | 2022-08-29
|  | Update | [7 empty] | 12 |  |  |  |  | 1 | 13
|  | List | [7 empty] | 12 |  |  |  |  | 0.5 | 12.5
|  | Search | [7 empty] | 4 |  |  |  |  | 1 | 5
23 | Payment Adjustment | Payment Verify -> Filter/Search | 4 | [9 empty] | 1 |  |  | 5 | 2022-09-01 | 2022-09-03
|  | Payment Verify -> Verify Action Download | 5 | [9 empty] | 0.5 |  |  | 5.5
24 |  | Payment Adjustment -> Adjustment List | 12 | [9 empty] | 0.5 |  |  | 12.5 | 2022-08-31 | 2022-09-01
|  | Payment Adjustment -> Filter/Search | 4 | [9 empty] | 1 |  |  | 5
|  | Payment Adjustment -> Excel Export | 1 | [9 empty] | 0.75 |  |  | 1.75
|  | Payment Adjustment -> Adjustment Detali | 10 | [9 empty] | 0.5 |  |  | 10.5
|  | Payment Adjustment -> Adjustment Submit | 6 | [9 empty] | 0.5 |  |  | 6.5
|  | Payment Adjustment -> Adjustment History | 6 | [9 empty] | 0.5 |  |  | 6.5
|  | Payment Adjustment -> History Excel Export | 1 | [9 empty] | 0.75 |  |  | 1.75
25 |  | ORD Settlement -> Payment List | 12 | [9 empty] | 0.5 |  |  | 12.5 | 2022-09-05 | 2022-09-06
|  | ORD Settlement -> Filter/Search | 3 | [9 empty] | 1 |  |  | 4
|  | ORD Settlement -> Excel Export | 1 | [9 empty] | 0.75 |  |  | 1.75
|  | ORD Settlement -> Action Submit | 8 | [9 empty] | 0.5 |  |  | 8.5
26 |  | Credit/Debit Note -> List View | [5 empty] | 6 |  |  |  |  | 0.5 |  |  | 6.5 | 2022-09-04 | 2022-09-05
|  | Credit/Debit Note -> Filter/Search | [5 empty] | 4 |  |  |  |  | 1 |  |  | 5
|  | Credit/Debit Note -> View Details(Ledger) | [5 empty] | 6 |  |  |  |  | 1 |  |  | 7
|  | Credit/Debit Note -> Credit Note Create | [5 empty] | 5 |  |  |  |  | 2 |  |  | 7
|  | Credit/Debit Note -> Debit Note Create | [5 empty] | 5 |  |  |  |  | 2 |  |  | 7
|  | Credit/Debit Note -> Approvals List | [5 empty] | 4 |  |  |  |  | 1 |  |  | 5
|  | Credit/Debit Note -> Approvals Summery | [5 empty] | 6 |  |  |  |  | 0.5 |  |  | 6.5
|  | Credit/Debit Note -> Approvals Activity | [5 empty] | 4 |  |  |  |  | 0.5 |  |  | 4.5
27 | Production -> Batch Preparation | List |  |  | 20 | [8 empty] | 0.5 |  | 20.5 | 2022-09-08 | 2022-09-10
|  | Create |  |  |  |  | 8 | [6 empty] | 2 |  | 10
|  | View (Stock Data) |  |  | 32 | [8 empty] | 1 |  | 33
|  | View (Batches & QR Code) |  |  | 24 | [8 empty] | 1 |  | 25
|  | View (QR) |  |  | 8 | [8 empty] | 0.5 |  | 8.5
28 | Inventory -> Stock | Stock Data -> List |  |  | 8 | [7 empty] | 0.5 |  |  | 8.5 | 2022-09-14 | 2022-09-15
|  | Stock Data -> View |  |  | 8 | [7 empty] | 0.5 |  |  | 8.5
0
29 |  | Sales Order -> Sales Booking -> List | [6 empty] | 12 |  |  |  | 0.5 |  |  | 12.5 | 2022-09-05 | 2022-09-06
|  | Sales Order -> Sales Booking -> Approval |  |  |  | 16 |  |  | 24 |  |  |  | 2 |  |  | 42
|  | Sales Order -> Sales Booking -> Tickets |  |  |  | 12 |  |  | 16 |  |  |  | 2 |  |  | 30
0
30 |  | Sales Order -> Sales Order -> List |  | 8 |  | 8 | [6 empty] | 0.5 |  |  | 16.5 | 2022-09-06 | 2022-09-07
|  | Sales Order -> Sales Order -> Add Order |  | 24 |  | 16 | [6 empty] | 3.5 |  |  | 43.5
|  | Sales Order -> Sales Order -> View |  | 16 |  | 12 | [6 empty] | 1 |  |  | 29
0
31 |  | Sales Order -> Picking -> List |  |  |  | 8 |  | 12 |  |  |  |  | 0.5 |  |  | 20.5 | 2022-09-26 | 2022-09-27
|  | Sales Order -> Picking -> Create |  |  |  | 16 |  | 24 |  |  |  |  | 3.5 |  |  | 43.5
|  | Sales Order -> Picking -> View |  |  |  | 12 |  | 16 |  |  |  |  | 1 |  |  | 29
0
32 |  | Sales Order -> Delivery Challan -> List |  |  |  | 8 |  |  | 12 |  |  |  | 0.5 |  |  | 20.5 | 2022-09-14 | 2022-09-15
|  | Sales Order -> Delivery Challan -> Create |  |  |  | 16 |  |  | 24 |  |  |  | 3.5 |  |  | 43.5
|  | Sales Order -> Delivery Challan -> View |  |  |  | 12 |  |  | 16 |  |  |  | 1 |  |  | 29
0
33 |  | Sales Order -> Invoices -> List |  |  |  | 8 |  | 12 |  |  |  |  | 0.5 |  |  | 20.5 | 2022-09-15 | 2022-09-18
|  | Sales Order -> Invoices -> Create |  |  |  | 16 |  | 24 |  |  | 4 |  | 3.5 |  |  | 47.5
|  | Sales Order -> Invoices -> View |  |  |  | 12 |  | 16 |  |  | 8 |  | 1 |  |  | 37
34 | Stock -> Transfer | Production Receive -> List |  |  |  | 4 |  |  | 12 |  | 4 |  | 1 |  |  |  | 2022-09-21 | 2022-09-22
|  | Production Receive -> Create |  |  |  | 8 |  |  | 12 |  | 4 |  | 3
|  | Production Receive -> View |  |  |  | 4 |  |  | 16 |  | 4 |  | 1
35 |  | Inventory Transfer -> List |  |  | 12 | 4 |  |  |  |  | 4 |  | 1 |  |  |  | 2022-09-21 | 2022-09-22
|  | Inventory Transfer -> Create |  |  | 12 | 8 |  |  |  |  | 4 |  | 3
|  | Inventory Transfer -> View |  |  | 16 | 4 |  |  |  |  | 4 |  | 1
36 |  | Store Transfer -> List | 8 |  |  | 4 |  |  |  |  | 4 |  | 1 |  |  |  | 2022-09-11 | 2022-09-12
|  | Store Transfer -> Create | 12 |  |  | 8 |  |  |  |  | 4 |  | 3
|  | Store Transfer -> View | 12 |  |  | 4 |  |  |  |  | 4 |  | 1
37 |  | Damage Declaration -> List |  |  |  | 4 |  | 12 |  |  | 4 |  | 1 |  |  |  | 2022-10-03 | 2022-10-04
|  | Damage Declaration-> Create |  |  |  | 8 |  | 16 |  |  | 4 |  | 3
|  | Damage Declaration -> View |  |  |  | 4 |  | 12 |  |  | 4 |  | 1
38 |  | Sales Return -> List |  | 8 |  | 4 |  |  |  |  | 4 |  | 1 |  |  |  | 2022-10-05 | 2022-10-06
|  | Sales Return-> Receive |  | 12 |  | 8 |  |  |  |  | 4 |  | 3
|  | Sales Return -> View |  | 12 |  | 4 |  |  |  |  | 4 |  | 1
39 | Multi Layer Approval | Domain Design |  | 8 | [11 empty] | 8 | 2022-09-29 | 2022-10-02
|  | Create |  | 40 |  | 12 | [7 empty] | 2 |  | 54
|  | Update |  | 48 |  | 2 | [7 empty] | 1.5 |  | 51.5
|  | List |  | 16 |  | 8 | [7 empty] | 0.5 |  | 24.5
|  | Deatils View |  | 16 |  | 12 | [7 empty] | 1 |  | 29
40 | Configure | Bank -> Create | [7 empty] | 9 |  |  |  |  | 2 | 11 | 2022-08-31 | 2022-09-01
|  | Bank -> Update | [7 empty] | 5 |  |  |  |  | 1 | 6
|  | Bank -> List | [7 empty] | 6 |  |  |  |  | 0.25 | 6.25
|  | Bank -> Deatils View | [7 empty] | 4 |  |  |  |  | 0.5 | 4.5
41 |  | Branch -> Create | [7 empty] | 9 |  |  |  |  | 2 | 11 | 2022-09-05 | 2022-09-06
|  | Branch -> Update | [7 empty] | 5 |  |  |  |  | 1 | 6
|  | Branch -> List | [7 empty] | 6 |  |  |  |  | 0.25 | 6.25
|  | Branch -> Deatils View | [7 empty] | 4 |  |  |  |  | 0.5 | 4.5
42 |  | Bank Account -> Create | [7 empty] | 9 |  |  |  |  | 2 | 11 | 2022-09-08 | 2022-09-11
|  | Bank Account -> Update | [7 empty] | 5 |  |  |  |  | 1 | 6
|  | Bank Account -> List | [7 empty] | 6 |  |  |  |  | 0.25 | 6.25
|  | Bank Account -> Deatils View | [7 empty] | 4 |  |  |  |  | 0.5 | 4.5
43 |  | Currency-> Create | [7 empty] | 9 |  |  |  |  | 2 | 11 | 2022-09-13 | 2022-09-14
|  | Currency -> Update | [7 empty] | 5 |  |  |  |  | 1 | 6
|  | Currency -> List | [7 empty] | 6 |  |  |  |  | 0.25 | 6.25
|  | Currency -> Deatils View | [7 empty] | 4 |  |  |  |  | 0.5 | 4.5
44 |  | Designation -> Create | [7 empty] | 9 |  |  |  | 2 |  | 11 | 2022-09-15 | 2022-09-15
|  | Designation -> Update | [7 empty] | 5 |  |  |  | 1 |  | 6
|  | Designation -> List | [7 empty] | 6 |  |  |  | 0.25 |  | 6.25
|  | Designation -> Deatils View | [7 empty] | 4 |  |  |  | 0.5 |  | 4.5
45 |  | Department -> Create |  |  |  |  | 9 | [6 empty] | 2 |  | 11 | 2022-08-30 | 2022-08-31
|  | Department -> Update |  |  |  |  | 5 | [6 empty] | 1 |  | 6
|  | Department -> List |  |  |  |  | 6 | [6 empty] | 0.25 |  | 6.25
|  | Department -> Deatils View |  |  |  |  | 4 | [6 empty] | 0.5 |  | 4.5
46 |  | Store -> Create |  |  |  |  | 9 | [6 empty] | 2 |  | 11 | 2022-09-04 | 2022-09-05
|  | Store -> Update |  |  |  |  | 5 | [6 empty] | 1 |  | 6
|  | Store -> List |  |  |  |  | 6 | [6 empty] | 0.5 |  | 6.5
|  | Store -> Deatils View |  |  |  |  | 4 | [6 empty] | 0.5 |  | 4.5
47 |  | Unit of Measurement -> Create |  |  |  |  | 6 | [6 empty] | 2 |  | 8 | 2022-09-07 | 2022-09-08
|  | Unit of Measurement -> Update |  |  |  |  | 4 | [6 empty] | 1 |  | 5
|  | Unit of Measurement -> List |  |  |  |  | 4 | [6 empty] | 0.5 |  | 4.5
|  | Unit of Measurement -> Deatils View |  |  |  |  | 2 | [6 empty] | 0.5 |  | 2.5
48 |  | Pack Size -> Create |  |  |  |  | 6 | [6 empty] | 2 |  | 8 | 2022-09-12 | 2022-09-13
|  | Pack Size -> Update |  |  |  |  | 4 | [6 empty] | 1 |  | 5
|  | Pack Size -> List |  |  |  |  | 4 | [6 empty] | 0.5 |  | 4.5
|  | Pack Size -> Deatils View |  |  |  |  | 2 | [6 empty] | 0.5 |  | 2.5
49 | User Management | User -> Create |  |  |  |  | 12 | [5 empty] | 2 |  |  | 14 | 2022-09-20 | 2022-09-21
|  | User -> Update |  |  |  |  | 12 | [5 empty] | 1.5 |  |  | 13.5
|  | User -> List |  |  |  |  | 8 | [5 empty] | 0.5 |  |  | 8.5
|  | User -> Deatils View |  |  |  |  | 8 | [5 empty] | 1 |  |  | 9
50 |  | Role -> Create | [7 empty] | 8 |  |  | 2 |  |  | 10 | 2022-09-19 | 2022-09-20
|  | Role -> Update | [7 empty] | 8 |  |  | 1.5 |  |  | 9.5
|  | Role -> List | [7 empty] | 4 |  |  | 0.5 |  |  | 4.5
|  | Role -> Deatils View | [7 empty] | 4 |  |  | 1 |  |  | 5
51 |  | User Role Mapping -> Create | [7 empty] | 8 |  | 2 |  |  |  | 10 | 2022-09-22 | 2022-09-25
|  | User Role Mapping -> Update | [7 empty] | 4 |  | 1.5 |  |  |  | 5.5
|  | User Role Mapping -> List | [7 empty] | 4 |  | 0.5 |  |  |  | 4.5
|  | User Role Mapping -> Deatils View | [7 empty] | 4 |  | 1 |  |  |  | 5
52 |  | User Company Mapping -> Create | [7 empty] | 8 |  |  | 2 |  |  | 10 | 2022-09-27 | 2022-09-28
|  | User Company Mapping -> Update | [7 empty] | 4 |  |  | 1.5 |  |  | 5.5
|  | User Company Mapping -> List | [7 empty] | 4 |  |  | 0.5 |  |  | 4.5
|  | User Company Mapping -> Deatils View | [7 empty] | 4 |  |  | 1 |  |  | 5
53 |  | Permission -> Create | 12 | [8 empty] | 2 |  |  |  | 14 | 2022-09-25 | 2022-09-29
|  | Permission -> Update | 12 | [8 empty] | 1.5 |  |  |  | 13.5
|  | Permission -> List | 8 | [8 empty] | 0.5 |  |  |  | 8.5
|  | Permission -> Deatils View | 8 | [8 empty] | 1 |  |  |  | 9
|  | Permission Implementation | 32 | [9 empty] | 16 | 16 |  | 64 | 2022-09-25 | 2022-09-29
|  | Total | 183 | 216 | 230 | 358 | 172 | 245 | 182 | 228 | 96 | 10 | 109.75 | 73.5 | 24 | 1778.25

## Mobile Features
Sl no. | TestCase ID | Feature name | Actions | WBS Hours | Resource Name | Completed(%) | Exp. Completion Date (Development) | Exp.Test Server Release Date | Actual Test Server Release Date | QA Start Date | QA End Date | Testing Time (hrs) | Bug Number | Solved BUG | Release Date(Bug /Feedback fixing) | Regression/Retesting Start Date | Regression/Retesting End Date | Regression/Retesting Hour | Total Hour
1 | TC_SB_001-TC_SB_007 | Sales Booking | Create | 4 | Tamanna | 100 | 2022-08-14 | 2022-08-16 | 2022-08-20 |  |  |  | NGLSC-968, NGLSC-965, NGLSC-967, NGLSC-969, NGLSC-970, NGLSC-971, NGLSC-972, NGLSC-975,NGLSC-976,NGLSC-979,NGLSC-980, NGLSC-981, NGLSC-982,NGLSC-985,NGLSC-986,NGLSC-1012,NGLSC-1016,NGLSC-1017,NGLSC-1059 Rakib: BUG:NGLSC-1311
|  |  | Update |  |  | 80
|  |  | List |  |  | 100
|  |  | View |  |  | 100
|  |  | Search |  |  | 20
|  |  | Approval path |  |  | 0 | Later | Later
2 | TC_PC_001-TC_PC_010 | Payment Collection Main Task: NGLSC-483 | Create | 4 | Saifur | 100 | 2022-08-11 | 2022-08-14 | 2022-08-20 |  |  |  | NGLSC-1048, NGLSC-1052, NGLSC-1053, NGLSC-1057, NGLSC-1058, NGLSC-1070 Rakib: BUG:NGLSC-1274, NGLSC-1301, NGLSC-1303, NGLSC-1304 | NGLSC-1274,
|  |  | List |  |  | 60
|  |  | View |  |  | 50
|  |  | Search |  |  | 10
3 | TC_SR_001-TC_SR_010 | Sales Return | Create | 4 | Rakib | 75 | 2022-08-30 | 2022-08-31 | 2022-09-12 |  |  |  | Rakib BUG: NGLSC-1302,
|  |  | Update |  |  | 75
|  |  | List |  |  | 100
|  |  | View |  |  | 45
|  |  | Search |  |  | 55
|  |  | Approval path |  |  | 0 | Later | Later
4 |  | User Account | Home Page | 1 | Tamanna | 100 | Done | 2022-08-16 | 2022-09-12
|  |  | Companay Switching |  |  | 100
5 | TC_OC_001-TC_OC_003 | ORD Calculator | List Page | 2 | Rakib | 100 | Done | 2022-08-16 | 2022-08-20
|  |  | Entry Page |  |  | 100
|  |  | Detail View |  |  | 100
6 |  | Ledger | List Page | 1.5 | Saifur | 0 | 2022-08-18 | 2022-08-21 | 2022-09-02
|  |  | Filter/Serarch |  |  | 0
|  |  | Detail View |  |  | 0
7 |  | Products | List Page | 1.5 | Saifur | 0 | 2022-08-22 | 2022-08-23 | 2022-08-20 | 2022-09-14 | 2022-09-14 |  | NGLSC-1042, NGLSC-1043, NGLSC-1044
|  |  | Filter/Serarch |  |  | 0
|  |  | Detail View |  |  | 0
8 | TC_CL_001-TC_CL_005 | Credit Limit | List Page | 3 | Tamanna | 0 | 2022-08-29 | 2022-08-30
|  |  | Filter/Serarch |  |  | 0
|  |  | Create |  |  | 0
|  |  | Approval path |  |  | 0 | Later | Later
9 |  | Invoice Acknowledgement | List Page |  |  | 0
|  |  | Filter/Serarch |  |  | 0
|  |  | Create |  |  | 0
|  |  | Approval path |  |  | 0